## Sprint capacity estimate
STORY POINTS | [12 empty] | (**) working days in the sprint, for the single resource, total sprint days minus vacations
SPRINT CAPACITY ALLOCATION | [12 empty] | (***) working hours in sprint, working days * 8.5 * 80 % factor, the factor includes the time for the planning / review / stand ups
Total days in sprint (*) | 15
Resource | Assignee1 | Assignee2 | Assignee3 | Assignee4 | Assignee5 | Assignee6 | Assignee7 | Assignee8 | Assignee9 | Assignee10 | Assignee11 | Assignee12
Allocation % | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
PTO | 0 | 0 | 0 | 0 | 2 | 0 | 5 | 0 | 0 | 0 | 0 | 0
Working days in sprint (**) | 15 | 15 | 15 | 15 | 13 | 15 | 10 | 15 | 15 | 15 | 15 | 15
Working hours in sprint (***) | 102 | 102 | 102 | 102 | 88.4 | 102 | 68 | 102 | 102 | 102 | 102 | 102
Allocated hours in sprint | 2.5 | 34 | 62.75 | 42.45 | 50 | 21 | 0 | 17 | 50.5 | 60.25 | 20.75 | 127.5
Percentage Occupation | 2.451% | 33.33% | 61.52% | 41.62% | 56.56% | 20.59% | 0% | 16.67% | 49.51% | 59.07% | 20.34% | 125%
Project1-1886 | [10 empty] | 4 |  | Task title 1
Project1-690 | [10 empty] | 0 |  | Task title 2
Project1-992 | 0 | [11 empty] | Task title 3
Project1-1111 |  |  | 0 | [9 empty] | Task title 4
Project1-1144 |  |  | 0 | [9 empty] | Task title 5
Project1-1201 |  |  |  | 0 | [8 empty] | Task title 6
Project1-1294 | [10 empty] | 0 |  | Task title 7
Project1-1297 | [9 empty] | 0 |  |  | Task title 8
Project1-1304 | [5 empty] | 0 | [6 empty] | Task title 9
Project1-1327 | [10 empty] | 0 |  | Task title 10
Project1-1328 |  | 0 | [10 empty] | Task title 11
Project1-1329 |  | 0 | [10 empty] | Task title 12
Project1-1338 | [9 empty] | 0 |  |  | Task title 13
Project1-1370 | [10 empty] | 0 |  | Task title 14
Project1-1442 | [10 empty] | 0 |  | Task title 15
Project1-1458 | 0 | [11 empty] | Task title 16
Project1-1466 |  |  | 0 | [9 empty] | Task title 17
Project1-1468 | [6 empty] | 0 | [5 empty] | Task title 18
Project1-1480 | [6 empty] | 0 | [5 empty] | Task title 19
Project1-1482 | [10 empty] | 0 |  | Task title 20
Project1-1483 | [10 empty] | 0 |  | Task title 21
Project1-1485 | [10 empty] | 0 |  | Task title 22
Project1-1499 | [6 empty] | 0 | [5 empty] | Task title 23
Project1-1549 | [9 empty] | 0 |  |  | Task title 24
Project1-1564 | [6 empty] | 0 | [5 empty] | Task title 25
Project1-1565 | [5 empty] | 0 | [6 empty] | Task title 26
Project1-1568 | [5 empty] | 0 | [6 empty] | Task title 27
Project1-1570 | [6 empty] | 0 | [5 empty] | Task title 28
Project1-1576 | [10 empty] | 0 |  | Task title 29
Project1-1578 | [10 empty] | 0 |  | Task title 30
Project1-1595 | [10 empty] | 0 |  | Task title 31
Project1-1596 | [6 empty] | 0 | [5 empty] | Task title 32
Project1-1628 | [12 empty] | Task title 33
Project1-1645 | [10 empty] | 0 |  | Task title 34
Project1-1646 | [6 empty] | 0 | [5 empty] | Task title 35
Project1-1647 | 0 | [11 empty] | Task title 36
Project1-1651 | [10 empty] | 0 |  | Task title 37
Project1-1652 | [10 empty] | 0 |  | Task title 38
Project1-1655 | [10 empty] | 0 |  | Task title 39
Project1-1656 | [5 empty] | 0 | [6 empty] | Task title 40
Project1-1658 | [10 empty] | 0 |  | Task title 41
Project1-1666 | [6 empty] | 0 | [5 empty] | Task title 42
Project1-1667 | [5 empty] | 0 | [6 empty] | Task title 43
Project1-1677 | [9 empty] | 0.5 |  |  | Task title 44
Project1-1724 | 0 | [11 empty] | Task title 45
Project1-1739 | 0 | [11 empty] | Task title 46
Project1-1752 | [9 empty] | 0 |  |  | Task title 47
Project1-1755 | [10 empty] | 0 |  | Task title 48
Project1-1759 | [8 empty] | 0 |  |  |  | Task title 49
Project1-1760 |  |  | 0 | [9 empty] | Task title 50
Project1-1761 | [8 empty] | 0 |  |  |  | Task title 51
Project1-1762 |  |  | 0 | [9 empty] | Task title 52
Project1-1765 | [5 empty] | 0 | [6 empty] | Task title 53
Project1-1767 | 0 | [11 empty] | Task title 54
Project1-1772 | [12 empty] | Task title 55
Project1-1773 | [10 empty] | 0 |  | Task title 56
Project1-1777 | [6 empty] | 0 | [5 empty] | Task title 57
Project1-1780 | 0 |  | 0 | [9 empty] | Task title 58
Project1-1781 |  |  |  |  | 0 | [7 empty] | Task title 59
Project1-1785 | 0 | [11 empty] | Task title 60
Project1-1787 |  |  |  |  | 0 | [7 empty] | Task title 61
Project1-1789 | [10 empty] | 0 |  | Task title 62
Project1-1889 | [9 empty] | 0 |  |  | Task title 63
Project1-1890 | [9 empty] | 0 |  |  | Task title 64
Project1-1891 | [9 empty] | 0 |  |  | Task title 65
Project1-1892 |  | 0 | [10 empty] | Task title 66
Project1-1894 | [9 empty] | 0 |  |  | Task title 67
Project1-1895 | [10 empty] | 0 |  | Task title 68
Project1-1906 | [5 empty] | 0 | [6 empty] | Task title 69
Project1-1922 | [9 empty] | 0 |  |  | Task title 70
Project1-1786 |  | 34 | [10 empty] | Task title 71
Project1-1783 |  |  | 0 | 33.95 | 0 |  |  |  | 0 |  |  |  | Task title 72
Project1-1782 | [8 empty] | 17 |  |  |  | Task title 73
Project1-1756 | [9 empty] | 8 |  |  | Task title 74
Project1-1750 | 0 |  | 0 | [5 empty] | 19.5 |  |  |  | Task title 75
Project1-1748 | 0 |  | 0 |  |  | 21 | [6 empty] | Task title 76
Project1-1648 |  |  |  |  | 0 | [7 empty] | Task title 77
Project1-1641 |  |  |  |  | 0 | [7 empty] | Task title 78
Project1-1633 | 1.5 |  | 42.5 |  | 17 | [7 empty] | Task title 79
Project1-1614 | [9 empty] | 29.75 | 12.75 |  | Task title 80
Project1-1610 |  |  |  |  | 7.5 | [7 empty] | Task title 81
Project1-1609 | [5 empty] | 0 | [6 empty] | Task title 82
Project1-1605 |  |  | 7.5 | [9 empty] | Task title 83
Project1-1249 | 0.5 |  |  | 8.5 | [5 empty] | 13.5 |  |  | Task title 84
Project1-1927 | [5 empty] | 0 | [6 empty] | Task title 85
Project1-1893 |  | 0 | [10 empty] | Task title 86
Project1-1812 | [7 empty] | 17 | 14 |  |  |  | Task title 87
Project1-1788 |  |  |  |  | 17 | [7 empty] | Task title 88
Project1-1766 | [9 empty] | 8.5 |  |  | Task title 89
Project1-1749 | [11 empty] | 127.5 | Task title 90
Project1-1737 |  |  |  |  | 8.5 | [7 empty] | Task title 91
Project1-1727 |  |  | 12.75 | [9 empty] | Task title 92
Project1-1559 |  | 0 | [10 empty] | Task title 93
Project1-1278 | [10 empty] | 4 |  | Task title 94
Project1-718 | 0.5 | [11 empty] | Task title 95
Project1-687 | 0 |  |  |  |  | 0 |  |  |  | 0 |  |  | Task title 96

## Summary
Working days | Working hours | Allocated time
158 | 1074.4 | 361.2